## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-09-04 | Done | Philosophy of AI & Information literacy | Philosophy of AI & Information Literacy | Meeting | ILO 1.3 | 1.5 | 1.5 | 0
2023-09-05 | Done | DataLab I: Creative Brief | DataLab I: Creative Brief | Planning | ILO 1.3 | 2.5 | 1.5 | -1
2023-09-05 | Done | DataLab I: Creative Brief | Minority Report | Meeting | ILO 3.1 | 3 | 2 | -1
2023-09-05 | Done | DataLab I: Creative Brief | A day in a life of data scientist | Research | ILO 1.3 | 2.5 | 2 | -0.5
2023-09-06 | Done | History of AI & GitHub | History of artificial intellegence | Study | ILO 3.1 | 2 | 1.5 | -0.5
2023-09-06 | Done | History of AI & GitHub | github | Study | ILO 3.1 | 4 | 5 | 1
2023-09-07 | Done | Programming: Variables and Conditionals | programing variables and conditionals | Programming | ILO 5.1 | 4 | 4 | 0
2023-09-07 | Done | Programming: Variables and Conditionals | programing variables and conditionals | Programming | ILO 5.1 | 4 | 4 | 0
2023-09-08 | Done | DataLab II: Creative Brief & Presenting | Q & A stand up | Meeting | ILO 1.3 | 0.15 | 0.15 | 0
2023-09-08 | Done | DataLab II: Creative Brief & Presenting | Review independent study material (starts at 9:30) | Study | ILO 2.4 | 1 | 0.5 | -0.5
2023-09-08 | Done | DataLab II: Creative Brief & Presenting | Presenting | Study | ILO 2.4 | 1.5 | 3 | 1.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/tree/main/Feedbacks/the%20hıstory%20of%20AI%20mılestone
2023-09-08 | Done | DataLab II: Creative Brief & Presenting | Delivering a presentation | Research | ILO 2.4 | 3 | 2.5 | -0.5
2023-09-08 | Done | DataLab II: Creative Brief & Presenting | quiz | Study | ILO 1.3 | 2.5 | 2 | -0.5
|  |  |  | Total Hours |  | 31.65 | 29.65 | -2
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2023-09-12 | Done | Intelligent Agents and conversational AI | Introduction : intelligent agents and conversational AI | Study | ILO 1.3 | 1.5 | 1 | -0.5
2023-09-12 | Done | Intelligent Agents and conversational AI | intelligent agents | Study | ILO 1.3 | 2 | 2.5 | 0.5
2023-09-12 | Done | Intelligent Agents and conversational AI | conversational AI | Study | ILO 1.3 | 3.5 | 4 | 0.5
2023-09-13 | Done | creative brief and turing tes | Introduction Creative Brief & Turing Test | Study | ILO 1.3 | 0.35 | 0.45 | 0.1
2023-09-13 | Done | creative brief and turing tes | stand up | Meeting | ILO 1.3 | 0.15 | 0.15 | 0
2023-09-13 | Done | creative brief and turing tes | the turing test | Testing | ILO 3.1 | 2.5 | 2.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Turing%20test.png
2023-09-13 | Done | creative brief and turing tes | a day of a life of a analytics translator | Research | ILO 2.4 | 1 | 0.45 | -0.55
2023-09-13 | Done | creative brief and turing tes | ILO walkthrough | Meeting | ILO 1.3 | 1.5 | 1
2023-09-14 | Done | Taxonomy of AI | Introduction taxonomy of AI | Study | ILO 1.3 | 1 | 1.35
2023-09-14 | Done | Taxonomy of AI | data camp courses | Research | ILO 3.1 | 4 | 4.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Introdyction%20to%20data.png
2023-09-14 | Done | Taxonomy of AI | data analysis | Study | ILO 3.1 | 2 | 2.5 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Introduction%20to%20data%20literacy.png
2023-09-15 | Done | Programming: Functions and Loop | Programming: Functions and Loop | Programming | ILO 5.1 | 7 | 7
2023-09-16 | Done | DataLab II: Creative Brief & Feedbac | introduction :creative brief and feedback | Study | ILO 1.3 | 0.15 | 0.15
2023-09-16 | Done | DataLab II: Creative Brief & Feedbac | stand up | Meeting | ILO 1.3 | 0.15 | 0.15
2023-09-16 | Done | DataLab II: Creative Brief & Feedbac | Review independent study materia | Evidencing | ILO 3.1 | 0.45 | 0.45 | 0
2023-09-16 | Done | DataLab II: Creative Brief & Feedbac | Feedback | Research | ILO 2.4 | 3 | 4 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/CertificateOfCompletion_Giving%20and%20Receiving%20Feedback.pdf
2023-09-16 | Done | DataLab II: Creative Brief & Feedbac | practice time : feedback workshop | Workshop | ILO 2.4 | 1 | 0.5
2023-09-16 | Done | DataLab II: Creative Brief & Feedbac | quizz | Study | ILO 1.3 | 1.5 | 2
|  |  |  | Total Hours |  | 32.75 | 34.65 | 1.9
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-09-18 | Done | Taxonomy of AI II & State-of-the-art AI | introduction | Planning | ILO 1.3 | 0.2 | 0.15 | -0.05
2023-09-18 | Done | Taxonomy of AI II & State-of-the-art AI | Taxonomy of AI: Domains, subdomains, and keywords | Study | ILO 1.3 | 4 | 3.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Tasks/Domain%20and%20subdomains%20in%20AI.jpg | In this part we get to know more about AI domains and Subdomains
2023-09-18 | Done | Taxonomy of AI II & State-of-the-art AI | State-of-the-art AI | Study | ILO 1.3 | 3.5 | 4 | 0.5
2023-09-19 | Done | Creative Brief | Q&A and Standup | Meeting | ILO 1.3 | 0.15 | 0.2 | 0.05
2023-09-19 | Done | Creative Brief | a day of a life of a Data engineer | Research | ILO 1.3 | 0.45 | 0.5 | 0.05
2023-09-19 | Done | Creative Brief | quizz | Study | ILO 1.3 | 0.15 | 0.15 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Tasks/Creative%20brief%20quizz.png
2023-09-19 | Done | Creative Brief | Guest lectures | Lecture | ILO 1.3 | 1.5 | 1.5 | 0
2023-09-19 | Done | Creative Brief | DataLab tasks | Study | ILO 1.3 | 4 | 4.5 | 0.5
2023-09-20 | Done | Risks & Benefits of AI | Introduction to data ethics | Study | ILO 1.3 | 4 | 3.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Tasks/IntroToDataEthicsModule1%20Copy.pdf
2023-09-20 | Done | Risks & Benefits of AI | Introduction to data ethics 2 | Study | ILO 1.3 | 4 | 3.5 | -0.5 |  | I have learned in this section about the ethics in AI algorithms and the different uses of AI in benifitial way or bad using
2023-09-21 | Done | Data Structures I | strings | Programming | ILO 5.1 | 4 | 4 | 0
2023-09-21 | Done | Data Structures I | lists | Programming | ILO 5.1 | 4 | 4 | 0
2023-09-22 | Done | AI in Science Fiction' presentations | Q&A and Standup | Study | ILO 1.3 | 0.15 | 0.15 | 0
2023-09-22 | Done | AI in Science Fiction' presentations | Review independent study material | Study | ILO 1.3 | 0.5 | 0.4 | -0.1
2023-09-22 | Done | AI in Science Fiction' presentations | DATA lab task finalizing | Study | ILO 3.1 | 3 | 4 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/deliverables/AI%20in%20Minority%20Report.pdf
2023-09-22 | Done | ‘AI in Science Fiction' presentations | presentaion | Evidencing | ILO 3.1 | 0.3 | 0.1 | -0.2 | https://edubuas-my.sharepoint.com/personal/234051_buas_nl/_layouts/15/stream.aspx?id=%2Fpersonal%2F234051%5Fbuas%5Fnl%2FDocuments%2FMicrosoft%20Teams%20Chat%20Files%2FPXL%5F20230922%5F112725537%2ETS%2Emp4&referrer=OfficeHome%2EWeb&referrerScenario=RecentVideo%2EView
|  |  |  | Total Hours |  | 33.9 | 34.15 | 0.25 |  | we were able to make a presnetaion and give a feed back on what we had learned on this block
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] |  | Bad time management is my main concern
2023-09-25 | Done | Quantifying our World into Data | Data Science Introduction Lecture | Lecture | ILO 1.3 | 1.15 | 1.25 | 0.1 |  | I was able to understand how to describe the data and give a data driven decision
2023-09-25 | Done | Quantifying our World into Data | Preparation for DataLab: | Study | ILO 1.3 | 1.5 | 2 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Tasks/231018_SDG%20indicators_week4datalab1.1.txt
2023-09-25 | Done | Quantifying our World into Data | What will you be doing for Data Science? | Study | ILO 1.3 | 2.5 | 1.2 | -1.3
2023-09-25 | Done | Quantifying our World into Data | 4) Workshop: Introduction to PowerBI | Study | ILO 4.1 | 2 | 2.3 | 0.3
2023-09-26 | Done | Datalab 00: SDG indicators | Stand-up | Study | ILO 1.3 | 0.15 | 0.15 | 0
26//9/23 | Done | Datalab 00: SDG indicators | Datalab Preparation review; Quantifying our World into Data | Study | ILO 1.3 | 1.5 | 0.45 | -1.05 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Tasks/the%20different%20ways%20you%20can%20get%20started%20writing%20your%20problem%20statement..txt
2023-09-26 | Done | Datalab 00: SDG indicators | SDG Lecture | Study | ILO 1.3 | 1 | 1.15 | 0.15
2023-09-26 | Done | Datalab 00: SDG indicators | Forming a Problem Statement | Study | ILO 1.3 | 1.5 | 1.3 | -0.2
2023-09-26 | Done | Datalab 00: SDG indicators | Forming a Research question | Study | ILO 1.3 | 1.5 | 1.3 | -0.2
2023-09-26 | Done | Datalab 00: SDG indicators | Writing an data-driven research question | Study | ILO 4.2 | 1 | 1.5 | 0.5
2023-09-26 | Done | Datalab 00: SDG indicators | Mentor Group discussion | Meeting | ILO 1.3 | 1 | 1 | 0
2023-09-27 | Done | Intro to Variables and Data Transformation | Introduction to concepts | Study | ILO 1.3 | 1 | 1 | 0 |  | I was able to finish the course of how to use "power bi"
2023-09-27 | Done | Intro to Variables and Data Transformation | Workshop | Study | ILO 1.3 | 6 | 6.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Introduction%20to%20Power%20BI.pdf
2023-09-27 | Done | Intro to Variables and Data Transformation | Datalab Preparation | Study | ILO 1.3 | 1 | 2.5 | 1.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Tasks/VariablesDatalabPreparation.pbix
2023-09-28 | Done | Data Structures II | Dictionaries.ipynb | Programming | ILO 5.1 | 4 | 4 | 0
2023-09-28 | Done | Data Structures II | Tuples.ipynb | Programming | ILO 5.1 | 4 | 4 | 0
2023-09-29 | Done | Datalab 01: Exploratory Data Analysis 1 | 1. Datalab Preparation Review: 0.5 Hours | Meeting | ILO 1.3 | 0.5 | 1 | 0.5
2023-09-29 | Done | Datalab 01: Exploratory Data Analysis 1 | 1. Exploratory Data Analysis workshop: 2-3 Hours | Study | ILO 1.3 | 3 | 3.5 | 0.5
2023-09-29 | Done | Datalab 01: Exploratory Data Analysis 1 | 1. Exploratory Data Analysis on SDG Indicators dataset: remaining hours | Research | ILO 1.3 | 3 | 4 | 1
2023-09-29 | Done | Datalab 01: Exploratory Data Analysis 1 | Day reflection | Meeting | ILO 1.3 | 0.5 | 0.2 | -0.3
|  |  |  | Total Hours |  | 37.8 | 40.3 | 2.5
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-10-02 | Done | Descriptive Analyses & Visualisations | Introduction to Descriptive Statistics | Study | ILO 1.3 | 0.5 | 0.4 | -0.1
2023-10-02 | Done | Descriptive Analyses & Visualisations | Hands-on Datacamp Course | Workshop | ILO 4.1 | 3 | 5 | 2 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/exploratory%20data%20analysis%20in%20power%20bi.pdf
2023-10-02 | Done | Descriptive Analyses & Visualisations | Introduction to Visualizations | Study | ILO 1.3 | 0.5 | 0.6 | 0.1
2023-10-02 | Done | Descriptive Analyses & Visualisations | Hands-on application | Workshop | ILO 4.1 | 3.5 | 4 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/data%20visualization%20in%20power%20bi.pdf
2023-10-02 | Done | Descriptive Analyses & Visualisations | DataLab Preparation | Study | ILO 1.3 | 0.5 | 0.4 | -0.1
2023-10-03 | Done | Datalab 02: Exploratory Data Analysis 2 | Standup with Mentor Group | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-03 | Done | Datalab 02: Exploratory Data Analysis 2 | DataLab Preparation Review | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-03 | Done | Datalab 02: Exploratory Data Analysis 2 | EDA on chosen SDG data | Research | ILO 1.3 | 2 | 2 | 0
2023-10-03 | Done | Datalab 02: Exploratory Data Analysis 2 | Guest Lecture (Fe.1.016 | Lecture | ILO 1.3 | 1 | 0.5 | -0.5
2023-10-03 | Done | Datalab 02: Exploratory Data Analysis 2 | Weeks 9, 10 Challenges Info | Lecture | ILO 1.3 | 0.5 | 0.2 | -0.3
2023-10-03 | Done | Datalab 02: Exploratory Data Analysis 2 | EDA on chosen SDG data | Research | ILO 1.3 | 2 | 3 | 1
2023-10-03 | Done | Datalab 02: Exploratory Data Analysis 2 | End of the day reflection | Meeting | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-04 | Done | Reporting and Visualising Data | General Data Reporting | Study | ILO 1.3 | 1.5 | 2 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/CertificateOfCompletion_Learning%20Data%20Science%20Tell%20Stories%20With%20Data.pdf
2023-10-04 | Done | Reporting and Visualising Data | Data Reporting in Power BI | Workshop | ILO 4.1 | 1.5 | 1.3 | -0.2 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Data%20Reporting%20in%20Power%20BI.png
2023-10-04 | Done | Reporting and Visualising Data | Advanced data visualizations | Study | ILO 4.1 | 1 | 1.5 | 0.5
2023-10-04 | Done | Reporting and Visualising Data | DataLab Preparation | Study | ILO 4.1 | 4 | 3 | -1
2023-10-05 | Done | Files and Data | Data analysis.ipynb | Programming | ILO 5.1 | 4 | 3 | -1
2023-10-05 | Done | Files and Data | Files.ipynb | Programming | ILO 5.1 | 4 | 3 | -1
2023-10-06 | Done | Findings & Data Visualisations | Standup with Mentor Group | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-06 | Done | Findings & Data Visualisations | DataLab Preparation Review | Study | ILO 1.3 | 1 | 1 | 0
2023-10-06 | Done | Findings & Data Visualisations | Feedback session | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-06 | Done | Findings & Data Visualisations | Enhancing your dashboard | Study | ILO 1.3 | 4 | 4 | 0
2023-10-06 | Done | Findings & Data Visualisations | End of the day reflection | Study | ILO 1.3 | 1 | 1 | 0
|  |  |  | Total Hours |  | 38 | 38.4 | 0.4
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] |  | not finishing on time , because I have a lot of work to do.
2023-10-09 | Done | Variability | Foundational Concepts of Variability | Study | ILO 1.3 | 1.5 | 1.3 | -0.2
2023-10-09 | Done | Variability | Introduction to Guided Case Study | Study | ILO 1.3 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Guided%20Case%20Study%20-%20Customer%20Churn.pdf
`9/10/23 | Done | Variability | DataLab Preparation | Study | ILO 1.3 | 1.5 | 1 | -3 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/tree/main/Tasks/Variability
2023-10-10 | Done | Datalab 05: Presenting and Storytelling with Data | Standup with Mentor Group | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-10 | Done | Datalab 05: Presenting and Storytelling with Data | DataLab Preparation Review | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-10 | Done | Datalab 05: Presenting and Storytelling with Data | Presentation skills Preparation | Study | ILO 1.3 | 2 | 2 | 0
2023-10-10 | Done | Datalab 05: Presenting and Storytelling with Data | Data Driven Story Telling | Workshop | ILO 1.3 | 2 | 2 | 0
2023-10-10 | Done | Datalab 05: Presenting and Storytelling with Data | Presentation skills (Continued | Study | ILO 1.3 | 2 | 2 | 0
2023-10-11 | Done | Analysing Relationships between Variable | Data Modeling in Power BI | Study | ILO 4.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Data%20modeling%20in%20power%20bi.png
2023-10-11 | Done | Analysing Relationships between Variable | Correlations - DataLab Preparation | Study | ILO 4.1 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Tasks/231018_IbrahimAbdo_CorrelationDatalabPreparation_Week6_Day3.pbix
2023-10-11 | Done | Analysing Relationships between Variable | Regression - DataLab Preparation | Study | ILO 4.1 | 1.5 | 1 | -0.5
2023-10-12 | Blocked | Algorithms | "Introduction to Algorithms" | Programming | ILO 5.1 | 2 | 0 | -2
2023-10-12 | Blocked | Algorithms | 11. Algorithms.ipynb | Programming | ILO 5.1 | 4 | 0 | -4
2023-10-13 | Done | DataLab II: Discussion | DataLab Preparation Review | Study | ILO 1.3 | 0.5 | 0.5
2023-10-13 | Done | DataLab II: Discussion | Feedback session on all 3 dashboards | Study | ILO 4.2 | 3 | 3
2023-10-13 | Done | DataLab II: Discussion | Guest Lecture | Lecture | ILO 1.3 | 1 | 1
2023-10-13 | Done | DataLab II: Discussion | Recommendations for future analyses | Study | ILO 1.3 | 2 | 2
2023-10-13 | Done | DataLab II: Discussion | In-Class discussion | Study | ILO 1.3 | 1 | 1
|  |  |  | Total Hours |  | 33.5 | 26.3 | -7.2
- Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-10-23 | Done | Explanatory versus Predictive Modelling and Writing a Conclusion | Difference between descriptive, predictive and explanatory analyses | Study | ILO 1.3 | 2 | 2 | 0
2023-10-23 | Done | Explanatory versus Predictive Modelling and Writing a Conclusion | Introduction to Big Data | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-23 | Done | Explanatory versus Predictive Modelling and Writing a Conclusion | Good and bad prediction | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-23 | Done | Explanatory versus Predictive Modelling and Writing a Conclusion | Reporting best practice | Study | ILO 1.3 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Report%20design%20in%20power%20bi.png
2023-10-23 | Done | Explanatory versus Predictive Modelling and Writing a Conclusion | Conclusio | Study | ILO 1.3 | 1 | 1 | 0
2023-10-23 | Done | Explanatory versus Predictive Modelling and Writing a Conclusion | Referencin | Study | ILO 1.3 | 1 | 1 | 0
2023-10-24 | Done | Datalab 05: Presenting and Storytelling with Data | Standup with Mentor Group | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-24 | Done | Datalab 05: Presenting and Storytelling with Data | DataLab Preparation Review | Study | ILO 1.3 | 0.5 | 0.5 | 0
2023-10-24 | Done | Datalab 05: Presenting and Storytelling with Data | Python Exam &Dashboard feedback | Testing | ILO 5.1 | 2 | 2 | 0
2023-10-24 | Done | Datalab 05: Presenting and Storytelling with Data | Writing a conclusion | Study | ILO 1.3 | 3.5 | 3.5 | 0
2023-10-24 | Done | Datalab 05: Presenting and Storytelling with Data | End of the day reflectio | Study | ILO 4.1 | 0.5 | 0.5 | 0
2023-10-25 | Done | Presenting and Storytelling with Data | 1. Workshop User-Oriented Design in Power BI: 3 hours | Study | ILO 4.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/user_oriented%20design%20in%20power%20bi.pdf
2023-10-25 | Done | Presenting and Storytelling with Data | Workshop on dashboard UX | Study | ILO 1.3 | 4 | 4 | 0
2023-10-26 | Delayed | Algorithms II - LeetCode | LeetCode and create an account. | Programming | ILO 5.1 | 4
2023-10-27 | Done | Datalab 06: CRISP-DM; Iteration | Standup with Mentor Group | Study | ILO 1.3 | 0.5 | 0.5
2023-10-27 | Done | Datalab 06: CRISP-DM; Iteration | Iterating using CRISP-DM | Study | ILO 4.1 | 4 | 4
|  |  |  | Total Hours |  | 29.5 | 25.5 | -4
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-10-30 | Done | Advanced Power BI | Know about the Data Analyst career track | Study | ILO 4.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Introduction%20to%20DAX%20in%20Power%20Bi.png
2023-10-30 | Done | Advanced Power BI | Intermediate Data Modelin | Study | ILO 4.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/certificates/Intermediate%20Data%20Modeling%20in%20Power%20BI.png
2023-10-30 | Done | Advanced Power BI | Advanced Power Bi | Study | ILO 4.1 | 1 | 1 | 0
2023-10-30 | Done | Advanced Power BI | Working on Dashboard | Study | ILO 4.1 | 1 | 1 | 0
2023-10-31 | Done | PowerBi Dashboard | Feedback session with peers | Meeting | ILO 4.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Feedbacks/pre-powerbi-final%20presentaion/3d9a0962-4ee6-4186-a868-7aabb57a1043.pdf
2023-10-31 | Done | PowerBi Dashboard | Iterating on my Dashboard | Study | ILO 4.1 | 3 | 3 | 0
2023-11-01 | Done | Final touches | Finalizing my working and learning log | Evidencing | ILOs | 4 | 4 | 0
2023-11-02 | Done | helping peers | providing help to others with their dashboard and their logs | Meeting | ILO 1.3 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai1-adsai-Ibrahimabdo231018/blob/main/Tasks/Helping%20peers%20in%20thier%20tasks.png
|  |  |  | Total Hours |  | 22 | 22 | 0
|  |  |  | Total hours this block |  | 259.1 | 250.95 | -8.15

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.3 | W1: 0 | 0
ILO 2.4 | [8 empty] | 0
ILO 3.1 | [8 empty] | 0
ILO 4.1 | [8 empty] | 0
ILO 4.2 | [8 empty] | 0
ILO 5.1 | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
Use a formula like this to get your data from Worklog sheet : =IFERROR(SUM(FILTER('Worklog_Tasks&Times'!$H$5:$H$14,'Worklog_Tasks&Times'!$F$5:$F$14=$B4)),0)

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.3
Unplanned | Meeting | ILO 2.4
Blocked | Programming | ILO 3.1
In-Progress | Research | ILO 4.1
Done | Testing | ILO 4.2
Delayed | Workshop | ILO 5.1
Cancelled | Planning
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break